## Test Cases
Test Case ID | Module | Test Scenario | Pre-conditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Priority | Bug ID | Date Tested
TC_001 | Login | Login succeeds with valid credentials | User is on the login page (saucedemo.com) | 1. Enter username 2. Enter password 3. Click Login | standard_user / secret_sauce | Products page (/inventory.html) opens and shows 6 products | Products page opened as expected | Pass | High |  | 2026-07-31
TC_002 | Login | Login fails with a wrong password | User is on the login page | 1. Enter valid username 2. Enter wrong password 3. Click Login | standard_user / wrongpass | Error shown: "Epic sadface: Username and password do not match any user in this service"; user stays on login page | Error shown: "Epic sadface: Username and password do not match any user in this service" | Pass | High |  | 2026-08-01
TC_003 | Login | Login fails with both fields blank | User is on the login page | 1. Leave username and password blank 2. Click Login | None | Error shown: "Epic sadface: Username is required"; user stays on login page | Error shown: "Epic sadface: Username is required" | Pass | Medium |  | 2026-08-01
TC_004 | Login | Locked-out user cannot log in | User is on the login page | 1. Enter locked_out_user 2. Enter password 3. Click Login | locked_out_user / secret_sauce | Error shown: "Epic sadface: Sorry, this user has been locked out."; user stays on login page | Error shown: "Epic sadface: Sorry, this user has been locked out." | Pass | High |  | 2026-08-01
TC_005 | Cart | Add one item to the cart | Logged in as standard_user, on Products page | 1. Click "Add to cart" under Sauce Labs Backpack | Item: Sauce Labs Backpack | Cart badge shows 1 and the button changes to "Remove" | Cart badge shows 1 | Pass | High |  | 2026-08-01
TC_006 | Cart | Remove an item from the cart page | Sauce Labs Backpack is the only item in the cart | 1. Click the cart icon 2. Click "Remove" next to Sauce Labs Backpack | Item: Sauce Labs Backpack | Backpack disappears from the cart list and the cart badge disappears (cart is empty) | Item disappears, badge count decreases | Pass | Medium |  | 2026-08-01
TC_007 | Cart | Add multiple items to the cart | Logged in, on Products page, cart is empty | 1. Add Sauce Labs Backpack 2. Add Sauce Labs Bike Light 3. Add Sauce Labs Bolt T-Shirt 4. Click the cart icon | Backpack, Bike Light, Bolt T-Shirt | Badge shows 3 and all 3 items are listed in the cart | Badge shows 3, all 3 items listed in cart | Pass | Medium |  | 2026-08-01
TC_008 | Checkout | Checkout information accepted with valid details | Sauce Labs Backpack in cart, on cart page | 1. Click Checkout 2. Enter first name, last name and postal code 3. Click Continue | John / Doe / 12345 | Overview page opens showing the item, payment info, shipping info, item total, tax and total | Moves to overview page with order summary | Pass | High |  | 2026-08-01
TC_009 | Checkout | Checkout fails with all fields blank | On checkout information page | 1. Leave all three fields blank 2. Click Continue | None | Error shown: "Error: First Name is required"; user stays on the information page | Error: First Name is required | Pass | Medium |  | 2026-08-01
TC_010 | Checkout | Complete an order | On checkout overview page | 1. Review the order 2. Click Finish | None | Checkout Complete page opens with the heading "Thank you for your order!" | Thank you for your order! Your order has been dispatched, and will arrive just as fast as the pony can get there! | Pass | High |  | 2026-08-01
TC_011 | Logout | Logout from the menu | Logged in as standard_user | 1. Click the hamburger menu 2. Click Logout | None | Login page is shown with empty username and password fields | Redirected to login page | Pass | High |  | 2026-08-01
TC_012 | Logout | Back button after logout does not show the Products page | Logged in as standard_user | 1. Click the hamburger menu and click Logout 2. Click the browser Back button | None | Products page is NOT shown; user stays on (or returns to) the login page | After logout and pressing the browser Back button: login page shown with error "Epic sadface: You can only access '/checkout-step-two.html' when you are logged in." Products page was not shown. Banner text clipped (see BUG_001) | Pass | High |  | 2026-10-10
TC_013 | Login | Login fails with a wrong username | User is on the login page | 1. Enter wrong username 2. Enter valid password 3. Click Login | wronguser / secret_sauce | Error: "Epic sadface: Username and password do not match any user in this service" | Error shown: "Epic sadface: Username and password do not match any user in this service". Banner text is clipped on the mobile screen (see BUG_001) | Pass | High |  | 2026-10-10
TC_014 | Login | Login fails with username filled and password blank | User is on the login page | 1. Enter username 2. Leave password blank 3. Click Login | standard_user / (blank) | Error: "Epic sadface: Password is required" | Error shown: "Epic sadface: Password is required" | Pass | Medium |  | 2026-10-10
TC_015 | Login | Login fails with username blank and password filled | User is on the login page | 1. Leave username blank 2. Enter password 3. Click Login | (blank) / secret_sauce | Error: "Epic sadface: Username is required" | Error shown: "Epic sadface: Username is required" | Pass | Medium |  | 2026-10-10
TC_016 | Login | Login rejected when both fields contain only spaces | User is on the login page | 1. Type 3 spaces in username 2. Type 3 spaces in password 3. Click Login | spaces only | Login is rejected with an error message; user stays on login page | Error shown: "Epic sadface: Username and password do not match any user in this service"; user stays on login page. Banner text clipped (see BUG_001) | Pass | Low |  | 2026-10-10
TC_017 | Login | Username is case-sensitive | User is on the login page | 1. Enter STANDARD_USER (capitals) 2. Enter valid password 3. Click Login | STANDARD_USER / secret_sauce | Login is rejected with the "do not match any user" error | Error shown: "Epic sadface: Username and password do not match any user in this service"; username is case-sensitive. Banner text clipped (see BUG_001) | Pass | Medium |  | 2026-10-10
TC_018 | Login | Enter key submits the login form | User is on the login page | 1. Enter valid username and password 2. Press the Enter key (do not click Login) | standard_user / secret_sauce | Products page opens | Pressed Enter without tapping Login; Products page opened | Pass | Low |  | 2026-10-10
TC_019 | Login | Password field is masked | User is on the login page | 1. Type a password in the password field | secret_sauce | Characters appear as dots, not as readable text | Password characters shown as dots, not readable text | Pass | Medium |  | 2026-10-10
TC_020 | Inventory | Six products are listed | Logged in as standard_user | 1. Open the Products page 2. Count the products | None | Exactly 6 products are shown, each with name, description, price and Add to cart button | 6 products shown, each with image, name, description, price and an Add to cart button | Pass | High |  | 2026-10-10
TC_021 | Inventory | Sort by Name (A to Z) | Logged in as standard_user, on Products page | 1. Open the sort dropdown 2. Select "Name (A to Z)" | None | First product is Sauce Labs Backpack; last is Test.allTheThings() T-Shirt (Red) | Order: Backpack, Bike Light, Bolt T-Shirt, Fleece Jacket, Onesie, Test.allTheThings() T-Shirt (Red). First = Backpack, last = Test.allTheThings() T-Shirt (Red) | Pass | Medium |  | 2026-10-10
TC_022 | Inventory | Sort by Name (Z to A) | Logged in as standard_user, on Products page | 1. Open the sort dropdown 2. Select "Name (Z to A)" | None | First product is Test.allTheThings() T-Shirt (Red); last is Sauce Labs Backpack | Order: Test.allTheThings() T-Shirt (Red), Onesie, Fleece Jacket, Bolt T-Shirt, Bike Light, Backpack. First = Test.allTheThings() T-Shirt (Red), last = Backpack | Pass | Medium |  | 2026-10-10
TC_023 | Inventory | Sort by Price (low to high) | Logged in as standard_user, on Products page | 1. Open the sort dropdown 2. Select "Price (low to high)" | None | First product is Sauce Labs Onesie ($7.99); last is Sauce Labs Fleece Jacket ($49.99) | Order: Onesie $7.99, Bike Light $9.99, Bolt T-Shirt $15.99, Test.allTheThings() T-Shirt $15.99, Backpack $29.99, Fleece Jacket $49.99. Two items priced $15.99 (Bolt T-Shirt, Test.allTheThings() T-Shirt Red) keep the same relative order. | Pass | Medium |  | 2026-10-10
TC_024 | Inventory | Sort by Price (high to low) | Logged in as standard_user, on Products page | 1. Open the sort dropdown 2. Select "Price (high to low)" | None | First product is Sauce Labs Fleece Jacket ($49.99); last is Sauce Labs Onesie ($7.99) | Order: Fleece Jacket $49.99, Backpack $29.99, Bolt T-Shirt $15.99, Test.allTheThings() T-Shirt $15.99, Bike Light $9.99, Onesie $7.99. Two items priced $15.99 (Bolt T-Shirt, Test.allTheThings() T-Shirt Red) keep the same relative order. | Pass | Medium |  | 2026-10-10
TC_025 | Inventory | Product detail page opens | Logged in as standard_user, on Products page | 1. Click the name "Sauce Labs Backpack" | Item: Sauce Labs Backpack | Detail page opens with the correct name, description, image and price $29.99 | Detail page opened with name Sauce Labs Backpack, description, image, price $29.99 and an Add to cart button | Pass | Medium |  | 2026-10-10
TC_026 | Cart | Cart price matches the inventory price | Logged in, on Products page | 1. Note the Backpack price 2. Add Backpack to cart 3. Open the cart | Item: Sauce Labs Backpack | Cart shows Backpack at $29.99, quantity 1 | Cart shows Sauce Labs Backpack, price $29.99, quantity 1, cart badge 1 | Pass | High |  | 2026-10-10
TC_027 | Cart | Cart keeps items after page refresh | Backpack is in the cart | 1. Open the cart page 2. Refresh the browser (F5 / pull down) | Item: Sauce Labs Backpack | Backpack is still listed in the cart and the badge still shows 1 | After refreshing the cart page, Sauce Labs Backpack is still listed ($29.99, quantity 1) and the badge still shows 1 | Pass | Medium |  | 2026-10-10
TC_028 | Cart | Continue Shopping returns to Products | User is on the cart page | 1. Click "Continue Shopping" | None | Products page opens | Products page opened; Backpack still shows Remove and the cart badge still shows 1 | Pass | Low |  | 2026-10-10
TC_029 | Cart | Remove an item from the Products page | Backpack added to cart | 1. On the Products page click "Remove" under Backpack | Item: Sauce Labs Backpack | Button changes back to "Add to cart" and the cart badge disappears | After Add to cart: badge showed 1 and button changed to Remove. After Remove: button changed back to Add to cart and the badge disappeared | Pass | Medium |  | 2026-10-10
TC_030 | Checkout | Checkout fails with last name blank | Backpack in cart, on checkout information page | 1. Enter first name 2. Leave last name blank 3. Enter postal code 4. Click Continue | John / (blank) / 12345 | Error: "Error: Last Name is required" | "Error: Last Name is required" shown; user stays on the information page; first name and postal code stay filled | Pass | Medium |  | 2026-10-10
TC_031 | Checkout | Checkout fails with postal code blank | Backpack in cart, on checkout information page | 1. Enter first and last name 2. Leave postal code blank 3. Click Continue | John / Doe / (blank) | Error: "Error: Postal Code is required" | "Error: Postal Code is required" shown; user stays on the information page; first and last name stay filled | Pass | Medium |  | 2026-10-10
TC_032 | Checkout | Special characters in name fields | Backpack in cart, on checkout information page | 1. Enter @#$% in first name and last name 2. Enter postal code 12345 3. Click Continue | @#$% / @#$% / 12345 | Application does not crash. Note whether it accepts or rejects the input and report if the behaviour looks wrong | App accepted @#$% in both name fields with postal code 12345; no crash; overview page opened (Item total $29.99, Tax $2.40, Total $32.39). No validation is applied to special characters in names | Pass | Low |  | 2026-10-10
TC_033 | Checkout | Cancel on information page returns to cart | Backpack in cart, on checkout information page | 1. Click Cancel | None | Cart page opens and the Backpack is still in the cart | Cancel opened the cart page; Sauce Labs Backpack (9.99, qty 1) is still in the cart and the badge shows 1 | Pass | Low |  | 2026-10-10
TC_034 | Checkout | Overview total equals item price plus tax | Backpack in cart, valid details entered, on overview page | 1. Read Item total, Tax and Total | Backpack $29.99 | Item total $29.99, Tax $2.40, Total $32.39 | Overview shows Item total: $29.99, Tax: $2.40, Total: $32.39 (29.99 + 2.40 = 32.39). Also shows SauceCard #31337 and Free Pony Express Delivery | Pass | High |  | 2026-10-10
TC_035 | Checkout | Cancel on overview page returns to Products | On checkout overview page | 1. Click Cancel | None | Products page opens | Products page opened; Backpack still in the cart (badge 1) | Pass | Low |  | 2026-10-10
TC_036 | Session | Direct URL without login is blocked | User is logged out (new browser tab) | 1. Open saucedemo.com/inventory.html directly without logging in | None | Login page shown with error: "Epic sadface: You can only access '/inventory.html' when you are logged in." | Redirected to the login page with error "Epic sadface: You can only access '/inventory.html' when you are logged in." Products page was not shown. Banner text clipped (see BUG_001) | Pass | High |  | 2026-10-10
TC_037 | Buggy user | problem_user: each product shows its own image | User is on the login page | 1. Login as problem_user 2. Look at the product images | problem_user / secret_sauce | Each product shows its own correct image | Logged in as problem_user. All 6 products show the same picture (a dog with a tennis ball) instead of their own product images | Fail | Medium | BUG_002 | 2026-10-10
TC_038 | Buggy user | problem_user: sorting works | User is on the login page | 1. Login as problem_user 2. Sort by Name (Z to A) 3. Check order | problem_user / secret_sauce | Products are re-ordered Z to A | Logged in as problem_user. Selected a different sort option: nothing changed on screen, the product order stayed the same (still Name A to Z) | Fail | Medium | BUG_006 | 2026-10-10
TC_039 | Buggy user | problem_user: add to cart and remove work for all items | User is on the login page | 1. Login as problem_user 2. Click Add to cart on each of the 6 products 3. Click Remove on each | problem_user / secret_sauce | Every item is added (badge reaches 6) and every item can be removed | Logged in as problem_user. Tapped Add to cart on all 6 products: only 3 changed to Remove (Backpack, Bike Light, Onesie) and the cart badge showed 3. Tapping Remove did not work | Fail | High | BUG_004 | 2026-10-10
TC_040 | Buggy user | problem_user: checkout with valid details reaches overview | User is on the login page | 1. Login as problem_user 2. Add Backpack and go to Checkout 3. Enter John / Doe / 12345 4. Click Continue | problem_user / secret_sauce | Fields keep the values typed and the overview page opens | Logged in as problem_user. Last Name field cannot be typed into and stays empty. After tapping Continue: "Error: Last Name is required"; user cannot proceed to the overview page | Fail | High | BUG_003 | 2026-10-10
TC_041 | Buggy user | error_user: complete an order | User is on the login page | 1. Login as error_user 2. Add Backpack, go to Checkout 3. Enter valid details, Continue, Finish | error_user / secret_sauce | Order completes and the Thank you page appears | Logged in as error_user. Last Name field could not be typed into, yet Continue still opened Checkout: Overview ($29.99, tax $2.40, total $32.39) with no error. Tapping Finish then did nothing and the order was not completed | Fail | High | BUG_005, BUG_007 | 2026-10-10
TC_042 | Buggy user | performance_glitch_user: login speed | User is on the login page | 1. Login as performance_glitch_user 2. Note how long the Products page takes to appear | performance_glitch_user / secret_sauce | Products page appears within about 3 seconds | performance_glitch_user logged in successfully; login took about 2-3 seconds, then Products page opened | Pass | Medium |  | 2026-10-10
TC_043 | Login | Long error message is fully visible on a mobile screen | User is on the login page on a phone (Chrome mobile) | 1. Enter username alakazam 2. Enter password secret_sauce 3. Tap Login | alakazam / secret_sauce | The full error message is readable inside the red banner (no clipped lines) | Banner fits only two lines; the first and last lines of "Epic sadface: Username and password do not match any user in this service" are cut off | Fail | Low | BUG_001 | 2026-10-10

## Bug Reports
Bug ID | Related Test Case ID | Title / Summary | Environment | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Status | Evidence (screenshot link) | Date Found
BUG_001 | TC_043 (also seen in TC_013, TC_016, TC_017, TC_012) | Long login error message is clipped inside the red banner on mobile | Chrome on Android phone, saucedemo.com (phone layout and wider desktop-site layout) | 1. Open saucedemo.com 2. Enter username alakazam and password secret_sauce 3. Tap Login | Full error message is visible inside the banner | Banner fits only two lines; the top and bottom lines of the three-line message are cut off. Short messages (Username is required, Password is required) fit fine. Also seen with the long message "You can only access '/checkout-step-two.html' when you are logged in" (TC_012) in the wider layout, so it is not limited to the phone layout | Low | Low | Open | GitHub evidence folder (see README) | 2026-10-10
BUG_002 | TC_037 | All products show the same image for problem_user | Chrome on Android phone, saucedemo.com, user problem_user | 1. Open saucedemo.com 2. Login with problem_user / secret_sauce 3. Look at the Products page | Each product shows its own picture | All 6 products show the same picture (a dog holding a tennis ball) | Medium | Medium | Open | GitHub evidence folder (see README) | 2026-10-10
BUG_003 | TC_040 | Last Name cannot be entered on checkout information page for problem_user | Chrome on Android phone, saucedemo.com, user problem_user | 1. Login with problem_user / secret_sauce 2. Add any item and open the cart, tap Checkout 3. Type First Name John, try to type Last Name Doe, enter Postal Code 12345 4. Tap Continue | All three fields accept and keep the typed values; user moves to the overview page | Last Name field cannot be typed into and stays empty; Continue shows "Error: Last Name is required" and checkout is blocked | High | High | Open | GitHub evidence folder (see README) | 2026-10-10
BUG_004 | TC_039 | Add to cart and Remove do not work on all products for problem_user | Chrome on Android phone, saucedemo.com, user problem_user | 1. Login with problem_user / secret_sauce 2. Tap Add to cart on all 6 products 3. Tap Remove on the products | All 6 buttons change to Remove and the badge shows 6; Remove then changes them back and clears the badge | Only 3 products (Backpack, Bike Light, Onesie) changed to Remove and the badge showed 3. Tapping Remove did not work | High | Medium | Open | GitHub evidence folder (see README) | 2026-10-10
BUG_005 | TC_041 | Finish button does not complete the order for error_user | Chrome on Android phone, saucedemo.com, user error_user | 1. Login with error_user / secret_sauce 2. Add Sauce Labs Backpack, open cart, tap Checkout 3. Fill in the information and tap Continue 4. On the overview page tap Finish | Order completes and the Thank you for your order page opens | Tapping Finish does nothing; the order is not completed | Critical | High | Open | GitHub evidence folder (see README) | 2026-10-10
BUG_006 | TC_038 | Sorting does nothing for problem_user | Chrome on Android phone, saucedemo.com, user problem_user | 1. Login with problem_user / secret_sauce 2. Tap the sort dropdown and choose Name (Z to A) or a Price option | Products reorder according to the chosen option | Nothing changes on screen; the order stays the same | Medium | Medium | Open | No screenshot: the screen did not change after choosing a sort option | 2026-10-10
BUG_007 | TC_041 | Checkout continues without a Last Name for error_user | Chrome on Android phone, saucedemo.com, user error_user | 1. Login with error_user / secret_sauce 2. Add an item, open cart, tap Checkout 3. Enter First Name and Postal Code, try to type Last Name 4. Tap Continue | Last Name accepts typing; if left empty, the error "Last Name is required" appears | Last Name cannot be typed into, and Continue still opens the overview page with no error | High | Medium | Open | GitHub evidence folder (see README) | 2026-10-10

## Summary
Test Summary - SauceDemo
Metric | Value
Total test cases | 43
Passed | 37
Failed | 6
Executed (Pass + Fail) | 43
Not yet run / re-run | 0
Execution % | 100%
Pass % (of executed) | 86.05%
Bugs logged | 7
Critical + High bugs | 4
How to use this file
1. Light-yellow cells (Actual Result, Status, Bug ID, Date Tested) are the ones YOU fill after running each test on saucedemo.com.
2. Status choices: Pass, Fail, Blocked, Re-run. This summary updates by itself.
3. TC_001 to TC_011: only the Expected Result wording was fixed; your actual results were kept. TC_012 was rewritten and must be re-run.
4. TC_013 to TC_043 are new. Expected results are what SauceDemo should do; write what you really see in Actual Result.
5. If a buggy-user case (TC_037 to TC_042) behaves differently from Expected, set Status = Fail and log it in Bug Reports.
6. Dates in the old file (46234 / 46235) were Excel serial numbers; they are shown here as 31-Jul-2026 and 01-Aug-2026. Correct them if you ran the tests on other days.